## Cohort Space
STQA Unit Presentation — Cohort Space Task Database
Group_Name | Member_Name | Registration_Number | Task_Title | Status | Priority | Due_Date
Cohort Space | Kelvin Otieno Abidha | SCT212-0063/2023 | Project Proposal Writing | Done | High | 2025-03-10
Cohort Space | Cynthia Vaati Mbithi | SCT212-0050/2023 | Problem Statement Definition | Done | High | 2025-03-10
Cohort Space | Munene Josphat | SCT212-0346/2023 | Functional Requirements Specification | Done | High | 2025-03-10
Cohort Space | Dekow Mohamed | SCT212-0085/2023 | Non-Functional Requirements Specification | Done | Medium | 2025-03-10
Cohort Space | Kelvin Otieno Abidha | SCT212-0063/2023 | Hardware & Software Tools Selection | Done | Medium | 2025-03-10
Cohort Space | Cynthia Vaati Mbithi | SCT212-0050/2023 | UI/UX Wireframe Design (Figma) | Done | High | 2025-03-20
Cohort Space | Munene Josphat | SCT212-0346/2023 | Database Schema Design (PostgreSQL) | Done | High | 2025-03-20
Cohort Space | Dekow Mohamed | SCT212-0085/2023 | Frontend Development (React.js) | Done | High | 2025-04-05
Cohort Space | Kelvin Otieno Abidha | SCT212-0063/2023 | Backend API Development (Node.js) | Done | High | 2025-04-05
Cohort Space | Cynthia Vaati Mbithi | SCT212-0050/2023 | PIN-Protected Workspace (FR-01) | Done | High | 2025-04-10
Cohort Space | Munene Josphat | SCT212-0346/2023 | Resource Vault Implementation (FR-02) | Done | High | 2025-04-10
Cohort Space | Dekow Mohamed | SCT212-0085/2023 | Task Management Module (FR-03) | Done | High | 2025-04-15
Cohort Space | Kelvin Otieno Abidha | SCT212-0063/2023 | Milestone Tracking Feature (FR-04) | Done | Medium | 2025-04-15
Cohort Space | Cynthia Vaati Mbithi | SCT212-0050/2023 | Dashboard & Analytics (FR-05) | Done | Medium | 2025-04-20
Cohort Space | Munene Josphat | SCT212-0346/2023 | Selenium Automated Test Suite | Done | High | 2025-04-25
Cohort Space | Dekow Mohamed | SCT212-0085/2023 | Cross-Browser Compatibility Testing | Done | Medium | 2025-04-25
Cohort Space | Kelvin Otieno Abidha | SCT212-0063/2023 | Performance & Load Testing (NR-01) | Done | High | 2025-04-28
Cohort Space | Cynthia Vaati Mbithi | SCT212-0050/2023 | User Manual Documentation | Done | Medium | 2025-04-30
Cohort Space | Munene Josphat | SCT212-0346/2023 | Pre-Go Live Testing & Bug Fixes | In Progress | High | 2025-05-05
Cohort Space | Dekow Mohamed | SCT212-0085/2023 | Final Defense Presentation | To Do | High | 2025-05-10

## IoT Health Monitor
STQA Unit Presentation — Smart IoT Health Monitoring & Alert System Task Database
Group_Name | Member_Name | Registration_Number | Task_Title | Status | Priority | Due_Date
IoT Health Monitor | Shemiramoth Mugo | SCT212-0061/2023 | Project Proposal Writing | Done | High | 2026-03-10
IoT Health Monitor | Samuel Kuria | SCT212-0476/2023 | Problem Statement & Opportunity Analysis | Done | High | 2026-03-10
IoT Health Monitor | Lee Kariuki | SCT212-0049/2023 | Functional Requirements Specification | Done | High | 2026-03-10
IoT Health Monitor | Cecil Kioko | SCT212-0047/2023 | Non-Functional Requirements Specification | Done | Medium | 2026-03-10
IoT Health Monitor | Shemiramoth Mugo | SCT212-0061/2023 | Hardware Tools Selection (ESP32, Sensors) | Done | Medium | 2026-03-20
IoT Health Monitor | Samuel Kuria | SCT212-0476/2023 | Software Tools Selection (Arduino IDE, Firebase) | Done | Medium | 2026-03-20
IoT Health Monitor | Lee Kariuki | SCT212-0049/2023 | Circuit & Schematic Diagram Design | Done | High | 2026-03-25
IoT Health Monitor | Cecil Kioko | SCT212-0047/2023 | Database Schema Design (MySQL/Firebase) | Done | High | 2026-03-25
IoT Health Monitor | Shemiramoth Mugo | SCT212-0061/2023 | UI/UX Dashboard Wireframe Design | Done | High | 2026-03-28
IoT Health Monitor | Samuel Kuria | SCT212-0476/2023 | Microcontroller Programming (Arduino IDE) | In Progress | High | 2026-04-15
IoT Health Monitor | Lee Kariuki | SCT212-0049/2023 | Heart Rate Sensor Integration (FR-01/FR-03) | In Progress | High | 2026-04-15
IoT Health Monitor | Cecil Kioko | SCT212-0047/2023 | Temperature Sensor Integration (FR-02) | In Progress | High | 2026-04-15
IoT Health Monitor | Shemiramoth Mugo | SCT212-0061/2023 | Real-Time Data Display on OLED/Dashboard (FR-04) | To Do | High | 2026-04-20
IoT Health Monitor | Samuel Kuria | SCT212-0476/2023 | MQTT Protocol Data Transmission (FR-05) | To Do | High | 2026-04-22
IoT Health Monitor | Lee Kariuki | SCT212-0049/2023 | Historical Health Data Storage (FR-06) | To Do | Medium | 2026-04-25
IoT Health Monitor | Cecil Kioko | SCT212-0047/2023 | Alert System – OLED/Buzzer/Push Notification (FR-07) | To Do | High | 2026-04-25
IoT Health Monitor | Shemiramoth Mugo | SCT212-0061/2023 | Multi-Device Admin Monitoring (FR-09) | To Do | Medium | 2026-04-28
IoT Health Monitor | Samuel Kuria | SCT212-0476/2023 | Sensor Accuracy & Unit Testing | To Do | High | 2026-05-05
IoT Health Monitor | Lee Kariuki | SCT212-0049/2023 | Integration Testing – Sensor to Dashboard | To Do | High | 2026-05-05
IoT Health Monitor | Cecil Kioko | SCT212-0047/2023 | Alert Threshold Testing (JUnit/NUnit) | To Do | High | 2026-05-08
IoT Health Monitor | Shemiramoth Mugo | SCT212-0061/2023 | System Reliability & Performance Testing | To Do | Medium | 2026-05-10
IoT Health Monitor | Samuel Kuria | SCT212-0476/2023 | Technical Manual & User Guide Documentation | To Do | Medium | 2026-05-12
IoT Health Monitor | Lee Kariuki | SCT212-0049/2023 | Pre-Go Live Testing & Bug Fixes | To Do | High | 2026-05-14
IoT Health Monitor | Cecil Kioko | SCT212-0047/2023 | Final Defense Presentation | To Do | High | 2026-05-17

## SmartTraffic Vision
STQA Unit Presentation — SmartTraffic Vision Task Database
Group_Name | Member_Name | Registration_Number | Task_Title | Status | Priority | Due_Date
SmartTraffic Vision | Brian Kipkirui | SCT212-0057/2023 | Project Proposal Writing | Done | High | 2026-03-10
SmartTraffic Vision | Micah Sagero | SCT212-0056/2023 | Problem Statement & Opportunity Analysis | Done | High | 2026-03-10
SmartTraffic Vision | John Nyongesa | SCT212-0710/2022 | Functional Requirements Specification | Done | High | 2026-03-10
SmartTraffic Vision | Ian Mandila | SCT212-0162/2022 | Non-Functional Requirements Specification | Done | Medium | 2026-03-10
SmartTraffic Vision | Brian Kipkirui | SCT212-0057/2023 | Software Tools Selection (Python, OpenCV, YOLO) | Done | Medium | 2026-03-20
SmartTraffic Vision | Micah Sagero | SCT212-0056/2023 | Hardware Tools Selection (GPU Machine, IP Camera) | Done | Medium | 2026-03-20
SmartTraffic Vision | John Nyongesa | SCT212-0710/2022 | System Architecture Diagram (Draw.io/Lucidchart) | Done | High | 2026-03-25
SmartTraffic Vision | Ian Mandila | SCT212-0162/2022 | Database Design – PostgreSQL/MySQL Schema | Done | High | 2026-03-25
SmartTraffic Vision | Brian Kipkirui | SCT212-0057/2023 | UI Mockups for Alert & Report Dashboard | Done | High | 2026-03-28
SmartTraffic Vision | Micah Sagero | SCT212-0056/2023 | Video Stream Acquisition Module (FR-i) | In Progress | High | 2026-04-15
SmartTraffic Vision | John Nyongesa | SCT212-0710/2022 | Vehicle Detection & Classification – YOLO (FR-ii) | In Progress | High | 2026-04-15
SmartTraffic Vision | Ian Mandila | SCT212-0162/2022 | Object Tracking Across Frames (FR-iii) | In Progress | High | 2026-04-18
SmartTraffic Vision | Brian Kipkirui | SCT212-0057/2023 | Signal Jumping Violation Detection (FR-iv-a) | To Do | High | 2026-04-22
SmartTraffic Vision | Micah Sagero | SCT212-0056/2023 | Wrong-Way Driving Detection (FR-iv-b) | To Do | High | 2026-04-22
SmartTraffic Vision | John Nyongesa | SCT212-0710/2022 | Alert Generation & Evidence Capture (FR-v/FR-vi) | To Do | High | 2026-04-25
SmartTraffic Vision | Ian Mandila | SCT212-0162/2022 | Data Logging to Secure Database (FR-vii) | To Do | High | 2026-04-25
SmartTraffic Vision | Brian Kipkirui | SCT212-0057/2023 | Report Generation Module – Daily/Weekly/Monthly (FR-viii) | To Do | Medium | 2026-04-28
SmartTraffic Vision | Micah Sagero | SCT212-0056/2023 | Accuracy & Detection Rate Testing (≥90% target) | To Do | High | 2026-05-05
SmartTraffic Vision | John Nyongesa | SCT212-0710/2022 | Real-Time Performance & Latency Testing | To Do | High | 2026-05-05
SmartTraffic Vision | Ian Mandila | SCT212-0162/2022 | Robustness Testing (weather/lighting conditions) | To Do | Medium | 2026-05-08
SmartTraffic Vision | Brian Kipkirui | SCT212-0057/2023 | Security & Role-Based Access Testing | To Do | Medium | 2026-05-10
SmartTraffic Vision | Micah Sagero | SCT212-0056/2023 | Final Project Report & Documentation | To Do | Medium | 2026-05-12
SmartTraffic Vision | John Nyongesa | SCT212-0710/2022 | Pre-Go Live Testing & Bug Fixes | To Do | High | 2026-05-14
SmartTraffic Vision | Ian Mandila | SCT212-0162/2022 | Live Demonstration & Final Defense Presentation | To Do | High | 2026-05-17

## pochiWise
STQA Unit Presentation — PochiWise Task Database
Group_Name | Member_Name | Registration_Number | Task_Title | Status | Priority | Due_Date
PochiWise | Mercy Nzambi | SCT212-0058/2023 | Project Proposal Writing | Done | High | 2026-11-03
PochiWise | Adrian Kagambi | SCT212-0305/2023 | Functional Requirements Specification | Done | High | 2026-11-03
PochiWise | Kerry Nkiria | SCT212-0327/2023 | Non-Functional Requirements Specification | Done | Medium | 2026-11-03
PochiWise | Prudence Njogu | SCT212-0052/2030 | Competitor Analysis for Pochiwise | Done | Medium | 29/3/2026
PochiWise | Mercy Nzambi | SCT212-0058/2023 | UI/UX Wireframe Design | Done | Medium | 29/3/2026
PochiWise | Adrian Kagambi | SCT212-0305/2023 | Database Schema Design | Done | Medium | 30/3/2026
PochiWise | Kerry Nkiria | SCT212-0327/2023 | Backend Development Setup | Done | High | 16/4/2026
PochiWise | Prudence Njogu | SCT212-0052/2030 | API Structure Planning | Done | High | 16/4/2026
PochiWise | Mercy Nzambi | SCT212-0058/2023 | User Authentication | Done | High | 16/4/2026
PochiWise | Adrian Kagambi | SCT212-0305/2023 | Profile Management Feature | Done | Medium | 2026-04-05
PochiWise | Kerry Nkiria | SCT212-0327/2023 | Implementing the remaining features | Done | Medium | 2026-04-05
PochiWise | Prudence Njogu | SCT212-0052/2030 | Performance testing | Done | Medium | 2026-04-05
PochiWise | Mercy Nzambi | SCT212-0058/2023 | System Reliability & Performance Testing | Done | High | 2026-04-05
PochiWise | Adrian Kagambi | SCT212-0305/2023 | Testing & Bug Fixing | In Progress | High | 15/5/2026
PochiWise | Kerry Nkiria | SCT212-0327/2023 | User Manual & Documentation | In Progress | High | 15/5/2026
PochiWise | Prudence Njogu | SCT212-0052/2030 | Deployment & Go Live Preparation | In Progress | High | 15/5/2026

## MediRemind
STQA Unit Presentation — MediRemind Task Database
Group_Name | Member_Name | Registration_Number | Task_Title | Status | Priority | Due_Date
MediRemind | Jessy Cheruiyot | SCT212-0333/2023 | Project Proposal Writing | Done | High | 2026-12-03
MediRemind | Duncan maina | SCT212-0478/2023 | Healthcare Appointment System Requirement Gathering | Done | High | 2026-12-03
MediRemind | Gabriella Muthoni | SCT212-0330/2023 | Functional Requirements Specification | Done | High | 2026-12-03
MediRemind | Michael Kinyunzu | SCT212-0482/2023 | Non-Functional Requirements Specification | Done | High | 2026-12-03
MediRemind | Jessy Cheruiyot | SCT212-0333/2023 | Patient Appointment Workflow Design | Done | Medium | 2026-12-03
MediRemind | Duncan maina | SCT212-0478/2023 | Doctor Schedule Management Planning | Done | High | 29/3/2026
MediRemind | Gabriella Muthoni | SCT212-0330/2023 | UI/UX Design for Patient Dashboard | Done | Medium | 29/3/2026
MediRemind | Michael Kinyunzu | SCT212-0482/2023 | Database Schema Design for Appointments | Done | High | 29/3/2026
MediRemind | Jessy Cheruiyot | SCT212-0333/2023 | System Architecture & API Planning | Done | High | 16/4/2026
MediRemind | Duncan maina | SCT212-0478/2023 | Frontend Development Setup | Done | High | 16/4/2026
MediRemind | Gabriella Muthoni | SCT212-0330/2023 | Backend Development Setup | Done | High | 16/4/2026
MediRemind | Michael Kinyunzu | SCT212-0482/2023 | Patient Registration & Login Module | Done | Medium | 2026-04-05
MediRemind | Jessy Cheruiyot | SCT212-0333/2023 | Appointment Scheduling Feature | Done | High | 2026-04-05
MediRemind | Duncan maina | SCT212-0478/2023 | Doctor Availability Management Module | Done | High | 2026-04-05
MediRemind | Gabriella Muthoni | SCT212-0330/2023 | Automated SMS & Email Reminder Integration | In Progress | High | 2026-04-05
MediRemind | Michael Kinyunzu | SCT212-0482/2023 | Appointment Tracking & Reporting Module | In Progress | High | 15/5/2026
MediRemind | Jessy Cheruiyot | SCT212-0333/2023 | Centralized Admin Dashboard Development | Done | High | 15/5/2026
MediRemind | Duncan maina | SCT212-0478/2023 | Push Notification System Development | Done | High | 15/5/2026
MediRemind | Gabriella Muthoni | SCT212-0330/2023 | System Testing & Bug Fixing | To Do | Medium | 15/5/2026
MediRemind | Michael Kinyunzu | SCT212-0482/2023 | Deployment, Documentation & Go Live | To Do | High | 15/5/2026